## Sheet1
BUG Report
Project Name
Prepared By
Prepared Date
Reviewd By
Reviewd Date
Bug ID | Summary | Steps to Reproduce | Severity | priority | Status | Sceenshot/Note
BUG001 | Login allows invalid password | 1. Enter valid username. 2. Wrong password. 3.Click Login. | High | High | Open
BUG002 | Login allows empty fields | 1.Click login without entering username. 2.Click login without entering password. | High | High | Open
BUG003 | Signup allows existing username | Signup with an existing username | Medium | Medium | Open
BUG004 | Signup allows empty fields | 1.Click signup with empty. 2.Click signup with username. 3.Click signup with password. | Medium | Medium | Open
BUG005 | Signup allows short password | Enter password less than 6 characters | Medium | Medium | Open
BUG006 | Add to cart button not clickable | Click Add to Cart on mobile view | High |  | Open
BUG007 | Product quantity not updating in cart | Change quantity before adding to cart | High | High | Open
BUG008 | Product not removed from cart | Remove product from cart | High | High | Open
BUG009 | Total price in cart incorrect | Add multiple products and check total | High | High | Open
BUG010 | Checkout allows empty fields | Click checkout without entering details | High | High | Open
BUG011 | Invalid card accepted | Enter invalid credit card details | High | High | Open
BUG012 | Search shows wrong results | Search for an existing product | Medium | Medium | Open
BUG013 | Search shows no results incorrectly | Search for non-existing product | Low | Low | Open
BUG014 | Filter not working correctly | Filter products by category | Medium | Medium | Open
BUG015 | Sort products not correct | 1.Sort products low to high. 2. Sort products high to low | Medium | Medium | Open
BUG016 | Logout button not working | Click logout | High | High | Open
BUG017 | Logout button not working | Click logout | High | High | Open
BUG018 | Session does not timeout | Stay idle, session should expire | Medium | Medium | Open
BUG019 | Website layout broken on mobile | Open website on mobile | Medium | Medium | Open
BUG020 | Broken links on homepage | Click all links on homepage | Medium | Medium | Open
BUG021 | Product images not loading | Open product pages | Medium | Medium | Open
BUG022 | Checkout button not responding | Click checkout button | High | High | Open
BUG023 | Alerts missing for invalid actions | 1.Perform invalid login 2.Perform invalid signup. 3.Perform invalid cart actions. | Medium | Medium | Open
BUG024 | Homepage load time slow | Open homepage | Low |  | Open
BUG025 | Category navigation broken | Click category links | Medium | Medium | Open
BUG026 | Add to cart fails for some products | Add specific products | High | High | Open
BUG027 | Checkout confirmation missing | Complete checkout | High | High | Open
BUG028 | Mobile viewport buttons overlap | Open site on small screen | Medium | Medium | Open
BUG029 | Page scroll not smooth | 1.Scroll homepage. 2.Scroll product page. | Low | Low | Open
BUG030 | Alert messages misaligned | Trigger alert messages | Low | Low | Open